Title
Progress Report
Team 74

---
Long-term Goal
Introduction
- Diagnostic Tool
- REF: F08-74-DIAGTOOL
- Faculty Advisors:
  - Dr. Haibo Wang
  - Dr. Spyros Tragoudas

---
Introduction
- Team Members:
  - Joe Lenox, CE (Project Manager)
  - Douglas Palmer, EE
  - Wesley Tredinnick, EE
  - Mathew Morgan, CE
  - Nick Hamann, EE

---
Fulfilling Customer Needs
Outline
- Executive Summary, Joseph Lenox
- Discussion
  - Proposed Solutions and Accomplishments
  - Design Problems
  - The Plan
    - Changes
    - Time Line
    - RASI

---
Cost Analysis
Executive Summary
- Project Overview
  - Wireless Diagnostic Tool
- Major Design Changes
  - Change of Bluetooth Stack
  - Change of MCU
- Problems
  - Team member changes
  - Fine Print

---
Executive Summary

---
Strengths and Advantages
Overview

---
Power Management
- Dynamic operating frequency
  - In system programmable oscillator
  - Optimal performance
- Integrated rechargeable battery
  - 9V Li - Ion rechargeable
  - WT32 bluetooth transceiver
- Outlook
  - Components on order
  - Prototyping will not be delayed

---
PC Software
- Functionality concerns:
  - Must acquire data over serial port
  - Must process and display acquired data
  - Must provide control interface for field device
  - Pseudo-real-time
- Other concerns:
  - Cost
  - Licensing

---
PC Software – The Design

---
PC Software Progress

---
Next Steps of Action
Project Timeline
Description	Date	Status	Weeks	Range
Final Component Decision	2009-01-16	Incomplete	W1	01/12/09	01/16/09
All Schematics Complete	2009-01-30	Partial	W2	01/19/09	01/23/09
Design Verifications Complete	2009-02-06	Partial	W3	01/26/09	01/30/09
Begin prototyping subsystems	2009-02-20	Partial	W4	02/02/09	02/06/09
Finish Prototyping Subsystems	2009-02-27		W5	02/09/09	02/13/09
Systems Construction	2009-03-06		W6	02/16/09	02/20/09
Complete Interface Software	2009-03-20		W7	02/23/09	02/27/09
Systems Debugging	2009-03-27		W8	03/02/09	03/06/09
Begin Draft of Design Report	2009-04-03		W9	03/16/09	03/20/09
Give “end of project presentation.”	2009-04-10		W10	03/23/09	03/27/09
Oral Design Report Complete	2009-04-17		W11	03/30/09	04/03/09
Written Design Report Complete	2009-04-24		W12	04/06/09	04/10/09
	2009-04-24		W14	04/13/09	04/17/09
			W15	04/20/09	04/24/09
			W16	04/27/09	05/01/09
			W17	05/04/09	05/08/09

---
Project Responsibilities (RASI)

---
Summary
- Personnel Change early-on
- Approximately one week behind but moving quickly.
- No added resources required.