## Action Item List
PC-Based Modular Diagnostic Tools		Ref: FA08-74-DIAGTOOL					2009-04-02
#	Activity	Person	Assigned	Due Date	New Due Date	Status	Comments
1	Find a Faculty Technical Advisor	JL	18-9-08	19-9-08		100.00%	Dr. Tragoudas has agreed to be technical advisor
2	Research: Component Parts	DP	18-9-08	24-9-08		100.00%	5 pages for everything.
3	Research: Connectivity	TG	18-9-08	24-9-08	1-10-08	100.00%	Miscommunication with project manager, will take another week of research.
4	Research: Existing Commercial Products	WT	18-9-08	24-9-08	1-10-08	100.00%	Miscommunication with project manager, will take another week of research.
5	Research: Source Code Management	JL	18-9-08	24-9-08		100.00%	Looking into git and Subversion
6	Set up repository for documentation and (future) source	JL	18-9-08	24-9-08		100.00%	Git repository completed on server, instructions for use have been forwarded to team.
7	Research: Simulation Packages	JL	2008-09-18	2008-10-01		50.00%	Still looking into our options, this is a fairly long-term deal.
8	Compose Memo to Instructors	JL	18-9-08	2008-09-19		100.00%
9	Update and/or compile resume.	JL	18-9-08	2008-10-01		100.00%
10	Update and/or compile resume.	WT	18-9-08	2008-10-01		100.00%
11	Update and/or compile resume.	DP	18-9-08	2008-10-01		100.00%
12	Update and/or compile resume.	TG	2008-09-18	2008-10-01	2008-11-08	100.00%	Will have done when we get the proposal put together.
13	Compose Norms and Expectations	TG	18-9-08	2008-09-26		100.00%
14	Type Norms and Expectations Statement	TG	24-9-08	2008-09-26		100.00%
15	Literature Review – Final Composition	JL	2-10-08	2008-10-15		100.00%	Turned in to instructors.
16	Literature Review Section: Component Parts	DP	2-10-08	2008-10-13		100.00%
17	Literature Review Section: Existing Commercial Products	WT	2-10-08	2008-10-13		100.00%
18	Literature Review Section: Connectivity	TG	2-10-08	2008-10-13		100.00%
19	Demonstrate usage of Git	JL	8-10-08	2008-10-09		100.00%	Show the teammates interactively how to use Git
20	Write scripts to automate sending of required documents to instructors.	JL	2008-10-16	2008-10-22	N/A	Canceled	Not necessary anymore.
21	Update personal hours in the repository.	TG	2008-10-16	2008-10-17	N/A	Canceled	This is also a test to make sure people can use the repository correctly.
22	Update personal hours in the repository.	WT	2008-10-16	2008-10-17	N/A	Canceled	This is also a test to make sure people can use the repository correctly.
23	Update personal hours in the repository.	DP	2008-10-16	2008-10-17	N/A	Canceled	This is also a test to make sure people can use the repository correctly.
24	Research: Patents	JL	2008-10-22	2008-10-29	2008-11-02	100.00%	Haven't found much in the way of direct or extreme-near matches.
25	Research: Proposals	DP	2008-10-22	2008-10-29		100.00%
26	Subsystem: Connectivity	TG	2008-10-29	2008-11-05		100.00%
27	Multimeter (Ammeter, Voltmeter, Ohmeter) Acquisiton Hardware	WT	2008-10-29	2008-11-05	2008-11-09	100.00%	Joint Project with DP, 25V/1A, .1V/1mA
28	Logic Analysis / Oscilloscope Hardware	DP	2008-10-29	2008-11-05	2008-11-09	100.00%	Joint Project with WT, Square Wave/Sine Wave, 8bit on the LA
29	Literature Review Material: Data Acquisiton	DP	2008-10-29	2008-11-04	2008-11-09	100.00%	W/r/t the subsystem
30	Literature Review Material: Connections	TG	2008-10-29	2008-11-04	2008-11-09	100.00%	W/r/t the subsystem
31	Literature Review Material: Data Acquisiton	WT	2008-10-29	2008-11-04	2008-11-09	100.00%	W/r/t the subsystem
32	Move repository to github	JL	2008-11-04	2008-11-12		100.00%	Repository is now on secured 3rd-party hosting for $12/month.
33	PC-based data parsing	JL	2008-10-29	2008-11-05	2008-11-09	Canceled
34	Overall Interconnections	JL	2008-10-29	2008-11-06	2008-11-09	100.00%
35	Wireless prototyping kits (bluetooth)	TG	2008-10-30	2008-11-06	2008-11-09	100.00%
36	Presentation Slide Draft	DP	2008-11-12	2008-11-15		100.00%
37	Proposal final revisions	JL	2008-11-19	2008-12-04		100.00%
38	End of proposal memo draft	WT	2008-12-03	2008-12-04		100.00%
39	Executive Summary	DP	2008-12-03	2008-12-04		100.00%
40	Print proposal	JL	2008-12-03	2008-12-05		100.00%	Cost: $10.30
41	Compiling Team Memo to Instructors	WT	2009-01-15	2009-01-16		100.00%
42	Draft schematic for signal conditioning (O-scope)	WT	2009-01-15	2009-01-22	2009-02-12	100.00%	Schematic complete, needs some annotations still.
43	Draft schematic for signal conditioning (O-scope)	DP	2009-01-15	2009-01-22	2009-02-12	Canceled	Pulled Doug off of this (Wes is further ahead and they were working in parallel) to work on another spot.
44	Draft schematic for subcontroller datapath	JL	2009-01-15	2009-01-22	2009-02-18	90.00%	Runs from ADC to comm. Link; much more complicated that I expected it to be. Got most of it down on paper; still working out some of the “bugs” and getting the system together.
45	Fill out paperwork for ordering parts	JL	2009-01-15	2009-01-22		100.00%	Still have a lot of missing parts, have requested samples of some parts and completed paperwork for others. Waiting on rest of team. LabVIEW is in process.
46	Investigate LabView, ImageJ, Matlab as environments for software portion of project	NH	2009-01-29	2009-02-05		100.00%	Going to use GNU Octave (a MATLAB workalike) + Python scripts instead
47	Evaluate BlueGiga WT32 breakout for usage	DP	2009-02-05	2009-02-12		25.00%
48	Evaluate BlueGiga WT32 breakout for usage	MM	2009-02-05	2009-02-12		25.00%
49	Determine language/environment solution to use for custom data acquisition/processing/control software	NH	2009-02-05	2009-02-12		100.00%	Python/pySerial has been selected along with SWIG to incorporate C++ code that will call GNU Octave commands to perform signal processing.
50	Write data acquisition software	NH	2009-02-12	2009-03-05		100.00%
49	Update/create RASI for Progress Report	JL	2009-02-15	2009-02-18		100.00%	Almost complete, need to confirm a few details with other teammates. It has been incorporated with our AIL document.
50	Timeline for Progress Report	DP	2009-02-15	2009-02-18		100.00%	Complete, JL shifted things around.
51	Skeleton Memo for Progress Report	NH	2009-02-15	2009-02-18		100.00%	JL added a few notes to it as well
52	Update AIL download for course instructors	JL	2009-02-15	2009-02-27		100.00%	Weekly task for JL.
53	Check to see if LM3940s are on hand	WT	2009-02-19	2009-02-19		100.00%	quick check, not on hand
54	Signal Conditioner: Confirm a change of 9V input voltage	WT	2009-02-19	2009-02-27		100.00%	Don't need 9V as an input for the reference voltage
55	Construct signal conditioner	WT	2009-02-19	2009-02-27		75.00%	waiting on a part.
56	Learn how to control WT32 and pair a device	DP	2009-02-19	2009-02-27		0.00%
57	Mock output from file.	NH	2009-02-19	2009-02-27	2009-03-26	100.00%
58	Design clocking circuit	MM	2009-02-19	2009-02-27	On Hold	5.00%	Enhanced clock speed is not essential for prototype
59	Draw datapath schematic	JL	2009-02-19	2009-02-27		100.00%	Complete, may need further revisions later
60	Design power sub-system	MM	2009-02-19	2009-03-07		100.00%	Necessary parts ordered; charging schematic in progress
61	Assemble power sub-system	MM	2009-03-05	2009-03-13	2009-03-26	100.00%	Requires longevity testing
62	Display/Control Interface	NH	2009-03-05	2009-03-26		100.00%	Done until I come up with a better display mechanism.
63	Datapath: Main Control	JL	2009-03-05	2009-03-29		95.00%	Code has been written, compiled, loaded, some simulation.
64	Datapath USART shift	JL	2009-03-05	2009-03-29		95.00%	Code has been written, compiled, loaded, some simulation.
65	Rewrite of data acquisition for serial port	NH	2009-03-26	2009-04-09	2009-04-16	80.00%	Socket communication done, must finish writing pySerial code
66	Implement battery charging (USB); integrate power subsystem with WT-32	MM	2009-03-30	2009-04-02		100.00%	May use USB for configuring WT-32 as well
67	12VDC Reference voltage for Wes	MM	2009-03-26	2009-04-17		40.00%	Ready to build; need to buy a few odd sized passives
68	Drafting design report; gather cost data	MM	2009-04-02	2009-04-17		100.00%	Reporting on the power sub-system
69	Finish display/control interface	NH	2009-04-09	2009-04-16		100.00%
70	Write PC software subsystem description	NH	2009-04-16	2009-04-21		100.00%
71	Write Executive Summary of Design report	NH	2009-04-16	2009-04-21		100.00%
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329

## Team
PC-Based Modular Diagnostic Tools					Ref: FA08-74-DIAGTOOL					2009-04-02
				Hours Worked
Team Members	Major	Project / Manager	Shorthand	W1	W2	W3	W4	W5	W6	W7	W8	W9	W10	W11	W12	W13	W14	W15	W16	Total
Joseph Lenox	CpE/EE	X	JL	3.00	4.00	4.00	2.00	3.00	4.00	5.00	3.00	12.00	4.00	10.00					54
Doug Palmer			DP	5.00	8.00	5.00	3.00	6.00	3.00	8.00	0.00	0.00	0.00	0.00					38
Wesley Tredinnick			WT	3.00	6.00	3.00	1.00	6.00	3.00	8.00	0.00	0.00	0.00	0.00					30
				09/15/08	09/22/08	09/29/08	10/06/08	10/13/08	10/20/08	10/27/08	11/03/08	11/10/08	11/17/08	12/01/08

Joseph Lenox	CpE/EE	X	JL	0.00	0.00	5.00	3.00	5.00	7.00	0.00	2.00	0.00	2.00	7.00	6.00	10.00	2.00	7.00	3.00	59.00
Doug Palmer	EE		DP	0.00	3.00	5.00	2.00	4.00	5.00	3.00	5.00	0.00	3.00	4.00	3.00	4.00	4.00	6.00	0.00	51.00
Wesley Tredinnick	EE		WT	0.00	6.00	6.00	4.00	6.00	8.00	6.00	0.00	0.00	0.00	0.00	0.00	5.00	10.00	10.00	1.00	62.00
Matthew Morgan	CpE		MM	0.00	0.00	0.00	3.00	9.00	3.00	3.00	6.00	4.00	6.00	5.00	5.00	7.00	0.00	0.00	0.00	51.00
Nick Hamann			NH	0.00	0.00	2.00	4.00	8.00	4.00	0.00	6.00	3.00	0.00	4.00	4.00	6.00	20.00	0.00	3.00	64.00
				01/12/09	01/19/09	01/26/09	02/02/09	02/09/09	02/16/09	02/23/09	03/02/09	03/09/09	03/16/09	03/23/09	03/30/09	04/06/09	04/13/09	04/20/09	04/27/09

## Meeting Agendas
PC-Based Modular Diagnostic Tools				Ref: FA08-74-DIAGTOOL			04/02/09
Item ID	Meeting	AIL #	Description	Addressed	Notes
1	2008-10-22		Journals – their contents and the repository.	Y
2	2008-10-22		File format standardization	Y	JL: Suggest OpenOffice for our needs (free and works).
3	2008-10-22		C compilers and test-driven development	Y	JL: Recap last week's get-together.
4	2008-10-22		How to write Commit messages	Y	JL: Emphasize the formulaic style.
5	2008-10-22		Proposal – Discussion	Y
6	2008-10-23		Subsystems – Discussion	Y
7	2008-10-23		Git – Troubleshooting	Y
8	2008-10-30		Subsystems – Connections	Y
9	2008-10-30		Subsystems – Data Acquisition	Y
10	2008-10-30		Review AIL	Y
11	2008-11-05		Looking ahead, Winter Break 2008	Y
12	2008-11-05		Proposal review and checkup	Y
13	2008-11-05		AIL review.	Y
14	2008-11-05		Literature Review: ADC hardware	Y
15	2008-11-06		TG: Draft of connectivity	Y
16	2008-11-06		Review AIL	Y
17	2008-11-06		ADCs – rough estimate of requirements.	Y
18	2008-11-12		Review AIL	Y
19	2008-11-12		Review Draft proposal	Y
20	2008-11-12	35	Presentation	Y
21	2009-01-15		Lost TG, need to rebalance workload	Y	Cutting back to just an oscilloscope (with room to grow)
22	2009-01-15	45	Ordering parts, preliminary	Y	Parts are listed in design book
23	2009-01-15	41	Team Memo	Y	Wes is handling this.
24	2009-01-15		Review AIL	Y
25	2009-02-05		Part order update	Y	Ordered some parts for the team (controllers + muxes), need more requests ASAP
26	2009-02-05		BlueGiga breakout chip	Y	Found another Bluetooth chip that supports 2.0, EDR, etc. Is it worth it?
27	2009-02-05		Another meeting time?	Y	Should we pick another meeting time?
28	2009-02-05		AIL review.	Y
29	2009-02-05		E215 computer + keys	Y	Entire team needs to have access to that room + our locker.
30	2009-02-05		Doug's repository woes.	Y	Suggest that he clean out his SSH .known hosts file, call Joe after 6 to sort it out.
31	2009-02-05		LabVIEW/MATLAB alternatives – GNU Octave	Y	Nick wanted to examine a GNU tool for matlab – GNU Octave http://www.gnu.org/software/octave/
32	2009-02-05		Op-amp usage/clarification	Y	As per the design review, has the choice of the LF347 been looked into w/r/t using other opamps for the signal conditioner?
33	2009-02-05		Joe's Schedule Hell	Y	Joe needs to overload Tuesday some more. Is this acceptable?
34	2009-02-15		Chip Programmer	Y	The universal chip programmers in e230 work for our choice of microcontroller.
35	2009-02-15		Bluegiga breakout chip	Y	pins have been soldered to the chip
36	2009-02-15		Progress Reports	Y	Need someone to handle the individual parts of the progress report (timeline, rasi, etc)
37	2009-02-15		AIL review.	Y
38	2009-02-19		Retrospective: Written Progress Report	Y
39	2009-02-19	53	Voltage regulators?
40	2009-02-19		Bluetooth chip
41	2009-02-19		More components	Y	More stuff has been added to the locker
42	2009-02-19		Oral Progress Report	Y	Need a short presentation based
43	2009-02-19		Review: RASI
44	2009-02-19		Review: Timeline
45	2009-02-19		PC in E215
46	2009-02-19		9V	Y	Biggest battery can easily get ahold of is 9v, is this alright?
47	2009-03-19		Review: AIL	Y
48	2009-03-19		Schematics complete	Y
49	2009-03-19		Parts order update	Y
50	2009-03-19		rearranged locker	Y
51	2009-03-19		status of project	Y
52	2009-03-27		Project status, need to get going ASAP	Y
53	2009-03-27		Minimum test requirements	Y
54	2009-03-27		Updating hours (!)	Y
55	2009-03-27		Updating AIL.	Y
56	2009-03-27		Design report	Y
57	2009-04-02		AIL review.	Y
58	2009-04-02		Bluetooth!	Y
59	2009-04-16		Design report	Y
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173

## RASI
PC-Based Modular Diagnostic Tools					Ref: FA08-74-DIAGTOOL					2009-04-02
		RASI Chart					RASI Overview
Item #	Description	JL	MM	NH	WT	DP		Description	JL	MM	NH	WT	DP
1	Datapath: Probes to Ports	A			R	S		Datapath: Controls	R
2	Datapath: Ports to Controls	R					PC Interface
3	Datapath: Acquisition Unit Control	R	S		S
4	Datapath: Acquisition Unit Clocking/Synchronization	AS	R
5	Datapath: Controls to PC Interface		S			R
6	PC User Interface		S	R
7	Datapath: EXT port interface	A			R	S
8	Datapath: Acquisition Unit Performance Testing/Optimization	AS	R			S

## Project Timeline
PC-Based Modular Diagnostic Tools					Ref: FA08-74-DIAGTOOL					2009-04-02

#	Description	Date	Status	Weeks	Range
1	Final Component Decision	2009-01-16	Complete – W3	W1	01/12/09	01/16/09
2	All Schematics Complete	2009-01-30	Complete – W09	W2	01/19/09	01/23/09
3	Design Verifications Complete	2009-02-06	Complete – W10	W3	01/26/09	01/30/09
4	Begin prototyping subsystems	2009-02-20	Partial	W4	02/02/09	02/06/09
5	Finish Prototyping Subsystems	2009-02-27	Partial	W5	02/09/09	02/13/09
6	Systems Construction	2009-03-06	Partial	W6	02/16/09	02/20/09
7	Complete Interface Software	2009-03-20	Complete – W14	W7	02/23/09	02/27/09
8	Systems Debugging	2009-03-27	Partial	W8	03/02/09	03/06/09
				W9	03/16/09	03/20/09	03/09/09	03/13/09
				W10	03/23/09	03/27/09
9	Begin Draft of Design Report	2009-04-03	Complete – W14	W11	03/30/09	04/03/09
10	Give “end of project presentation.”	2009-04-10	Complete – W15	W12	04/06/09	04/10/09
11	Written Design Report Complete	2009-04-24	Complete – W15	W14	04/13/09	04/17/09
12	Oral Design Report Complete	2009-04-24	Complete – W15	W15	04/20/09	04/24/09
				W16	04/27/09	05/01/09
				W17	05/04/09	05/08/09

## Cost
PC-Based Modular Diagnostic Tools					Ref: FA08-74-DIAGTOOL					2009-04-02
Component/Service Cost
#	Date Ordered	Part #	Ordered By	Description	Quantity	Per/Unit	Total Cost		Total Part Cost:	$197.89
1	2009-02-25	COM-00534	JL	Crystal 20MHz	1	$1.50	$1.50
2	2009-02-25	COM-00316	JL	RS232 Converter DIP - MAX232 MAX3232	1	$1.95	$1.95
3	2009-02-25	COM-00526	JL	Voltage Regulator - 3.3V	1	$1.95	$1.95		Procedure for adding items:
4	2009-02-25	PRT-00115	JL	Break Away Female Headers	1	$1.50	$1.50		Copy the last line and change the values (Total Cost will auto-calculate)
5	2009-02-25	SH	JL	Shipping + Handling	1	$3.17	$3.17
6	2009-02-10	WRL-08952	JL	Bluetooth® Breakout - Bluegiga WT-32	1	$89.95	$89.95
7	2009-02-10	SH	JL	Shipping + Handling	1	$11.85	$11.85
8	2009-03-03	1N5818	MM	Schottky Diode	20	$0.14	$2.84
9	2009-03-03	1N4933	MM	Fast Recovery Power Rectifier	10	$0.05	$0.53
10	2009-03-03	106CKR050M	MM	Electrolytic Capacitor	10	$0.05	$0.45
11	2009-03-03	COM-00526	MM	Voltage Regulator - 3.3V	1	$1.95	$1.95
12	2009-03-03	COM-00527	MM	Voltage Regulator adjustable	1	$1.95	$1.95
13	2009-03-03	COM-08582	MM	Crystal 12MHz	1	$0.95	$0.95
14	2009-03-03	COM-00536	MM	Crystal 16MHz	1	$1.50	$1.50
15	2009-03-03	PRT-00091	MM	9V snap connector	1	$1.25	$1.25
16	2009-03-03	PRT-08613	MM	JST Vertical Connector	1	$0.95	$0.95
17	2009-03-03	PRT-08670	MM	JST Jumper Wire	1	$0.95	$0.95
18	2009-03-03	TOL-08734	MM	Barrel Jack to 2-pin JST	1	$2.95	$2.95
19	2009-03-03	TOL-00298	MM	Wall Adapter Power Supply – 9VDC	1	$5.95	$5.95
20	2009-03-03	PRT-09077	MM	Battery Charger 4 Bay	1	$9.95	$9.95
21	2009-03-03	IP-9V-500	MM	Ipower 500 mAh Li-Ion 9V Battery	1	$16.97	$16.97
22	2009-03-03	LT1073CN8	MM	MicroPower DC-DC Converter	2	$3.15	$6.30
23	2009-03-03	LT1073CN8-12	MM	MicroPower DC-DC Converter (12 VDC FIXED)	2	$3.15	$6.30
24	2009-03-03	LT1073CN8-5#PBF	MM	MicroPower DC-DC Converter (lead free)	2	$3.15	$6.30
25	2009-04-01	3.6V AA Lith. Bat	MM	Tadiran Lithium 3.6V	1	$16.99	$16.99
26	2009-04-01	AA Plastic Holder	MM	AA Plastic Holder	1	$0.99	$0.99
				$0.00
				$0.00
				$0.00
				$0.00
				$0.00
				$0.00
				$0.00
				$0.00
				$0.00
				$0.00