## Action Item List
PC-Based Modular Diagnostic Tools		Ref: FA08-74-DIAGTOOL					2008-10-30
#	Activity	Person	Assigned	Due Date	New Due Date	Status	Comments
1	Find a Faculty Technical Advisor	JL	18-9-08	19-9-08		100.00%	Dr. Tragoudas has agreed to be technical advisor
2	Research: Component Parts	DP	18-9-08	24-9-08		100.00%	5 pages for everything.
3	Research: Connectivity	TG	18-9-08	24-9-08	1-10-08	100.00%	Miscommunication with project manager, will take another week of research.
4	Research: Existing Commercial Products	WT	18-9-08	24-9-08	1-10-08	100.00%	Miscommunication with project manager, will take another week of research.
5	Research: Source Code Management	JL	18-9-08	24-9-08		100.00%	Looking into git and Subversion
6	Set up repository for documentation and (future) source	JL	18-9-08	24-9-08		100.00%	Git repository completed on server, instructions for use have been forwarded to team.
7	Research: Simulation Packages	JL	2008-09-18	2008-10-01		50.00%	Still looking into our options, this is a fairly long-term deal.
8	Compose Memo to Instructors	JL	18-9-08	19-9-08		100.00%
9	Update and/or compile resume.	JL	18-9-08	1-10-08		100.00%
10	Update and/or compile resume.	WT	18-9-08	1-10-08		100.00%
11	Update and/or compile resume.	DP	18-9-08	1-10-08		100.00%
12	Update and/or compile resume.	TG	2008-09-18	2008-10-01	2008-11-08	50.00%	Will have done when we get the proposal put together.
13	Compose Norms and Expectations	TG	18-9-08	26-9-08		100.00%
14	Type Norms and Expectations Statement	TG	24-9-08	26-9-08		100.00%
15	Literature Review – Final Composition	JL	2-10-08	15-10-08		100.00%	Turned in to instructors.
16	Literature Review Section: Component Parts	DP	2-10-08	13-10-08		100.00%
17	Literature Review Section: Existing Commercial Products	WT	2-10-08	13-10-08		100.00%
18	Literature Review Section: Connectivity	TG	2-10-08	13-10-08		100.00%
19	Demonstrate usage of Git	JL	8-10-08	9-10-08		100.00%	Show the teammates interactively how to use Git
20	Write scripts to automate sending of required documents to instructors.	JL	2008-10-16	2008-10-22		35.00%
21	Update personal hours in the repository.	TG	2008-10-16	2008-10-17		0.00%	This is also a test to make sure people can use the repository correctly.
22	Update personal hours in the repository.	WT	2008-10-16	2008-10-17		0.00%	This is also a test to make sure people can use the repository correctly.
23	Update personal hours in the repository.	DP	2008-10-16	2008-10-17		0.00%	This is also a test to make sure people can use the repository correctly.
24	Research: Patents	JL	2008-10-22	2008-10-29	11/02/08	50.00%	Haven't found much in the way of direct or extreme-near matches.
25	Research: Proposals	DP	2008-10-22	2008-10-29		0.00%
26	Subsystem: Connectivity	TG	2008-10-29	2008-11-05		0.00%
27	Multimeter (Ammeter, Voltmeter, Ohmeter) Acquisiton Hardware	WT	2008-10-29	2008-11-05		0.00%	Joint Project with DP, 25V/1A, .1V/1mA
28	Logic Analysis / Oscilloscope Hardware	DP	2008-10-29	2008-11-05		0.00%	Joint Project with WT, Square Wave/Sine Wave, 8bit on the LA
29	Literature Review Material: Data Acquisiton	DP	2008-10-29	2008-11-04		8.00%	W/r/t the subsystem
30	Literature Review Material: Connections	TG	2008-10-29	2008-11-04		5.00%	W/r/t the subsystem
31	Literature Review Material: Data Acquisiton	WT	2008-10-29	2008-11-04		3.00%	W/r/t the subsystem
32	PC-based data parsing	JL	2008-10-29	2008-11-05		0.00%
33	Overall Interconnections	JL	2008-10-29	2008-11-06		0.00%
34	Wireless prototyping kits (bluetooth)	TG	2008-10-30	2008-11-06		0.00%
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328

## Team
PC-Based Modular Diagnostic Tools					Ref: FA08-74-DIAGTOOL					2008-10-30
				Hours Worked
Team Members	Major	Project / Manager	Shorthand	W1	W2	W3	W4	W5	W6	W7	W8	W9	W10	W11	Total
Joseph Lenox	CpE/EE	X	JL	3.00	4.00	4.00	2.00	3.00	4.00	5.00	3.00	0.00	0.00	0.00	28
Tiffany Gallops			TG	2.00	5.00	3.00	2.00	6.00	3.00	9.00	0.00	0.00	0.00	0.00	30
Doug Palmer			DP	5.00	8.00	5.00	3.00	6.00	3.00	8.00	0.00	0.00	0.00	0.00	38
Wesley Tredinnick			WT	3.00	6.00	3.00	1.00	6.00	3.00	8.00	0.00	0.00	0.00	0.00	30
				09/15/08	09/22/08	09/29/08	10/06/08	10/13/08	10/20/08	10/27/08	11/03/08	11/10/08	11/17/08	12/01/08

## Meeting Agendas
PC-Based Modular Diagnostic Tools				Ref: FA08-74-DIAGTOOL			10/30/08
Item ID	Meeting	AIL #	Description	Addressed	Notes
1	2008-10-22		Journals – their contents and the repository.	Y
2	2008-10-22		File format standardization	Y	JL: Suggest OpenOffice for our needs (free and works).
3	2008-10-22		C compilers and test-driven development	Y	JL: Recap last week's get-together.
4	2008-10-22		How to write Commit messages	Y	JL: Emphasize the formulaic style.
5	2008-10-22		Proposal – Discussion	Y
6	2008-10-23		Subsystems – Discussion	Y
7	2008-10-23		Git – Troubleshooting	Y
8	2008-10-30		Subsystems – Connections	Y
9	2008-10-30		Subsystems – Data Acquisition	Y
10	2008-10-30		Review AIL	Y
11	2008-11-05		Looking ahead, Winter Break 2008
12	2008-11-05		Proposal review and checkup
13	2008-11-05		AIL review.
14	2008-11-05		Literature Review: ADC hardware
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173